## Timeline
|  |  |  | W2 |  |  |  |  | W3 | [6 empty] | W4
Task | Resource | Hours | Bus SO | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun
|  |  |  | 3 | 8 | 8 | 7 |  |  | 8 | 8 | 4 | 8
Accruals FS | JG | 3 | MS
Pricing Conditions FS | JG | 2 | EM
AP FS | JG | 2 | EK
AR FS | JG | 2 | EK
Pricing Conditions Actuals FS | JG | 4 | EM
Demand FS | JG | 2 | DJ
Business Signoff | JG | 6 | All
Accruals B&T | JG | 8 | MS
Pricing Condition B&T | JG | 4 | EM
AP B&T | JG | 4 | EK
AR B&T | JG | 4 | EK
Pricing Conditions Actuals B&T | JG | 1 | EM
Demand B&T | JG | 4 | DJ
Sense Check | JG | 8
[5 empty] | 8 | 8 | 8 |  |  | 8 | 4 |  | 8
Cust Validate and Build | CH | 1 | EM
Prod Validate and Build | CH | 1 | EM
Vendor Validate and Build | CH | 1 | EM
Sales Validate and Build | CH | 1 | EM
Cust Hier Investigate and Build | CH | 4 | EM
Prod Hier Investigate and Build | CH | 8 | EM
DF Table Maint Build | CH | 2 | EM
DF Extract Report Build | CH | 2 | DJ
Pricing Conditions Actuals B&T | CH | 16 | EM
Sense Check | CH | 8
Aims:
get interfacing complete to the stage where in UAT3 we're doing end to end testing on ALL interfaces.
Actions:
validate chris' timings
communicate to Drewy the plan
communicate to the business timings of SO and get agreement
Assumptions:
business allocate time to specs for review and prompt sign-off.
once specs are signed-off, there's no rework.
Risks:

## Interface List
ID | Interface Name | Promax interface number | Status | Resource | Priority | Source | Dest | In(to promax) / Out (from Promax) | Est Effort | Confirm Processes | Func Spec | Reviewed | Func Spec Signed Off | Dev Query | Dev Int | Transfer | Test | Tech Spec | Signoff | Test Data Source | Package Name | Filename | Int User Guide | Int Config | Master Data
1 | Product | 302 | Ready to test | Mal | 0 | LADS | PX | IN |  | 100% | 100% | 100% |  | 100% | 100% | 100% | 50% | 0% | 0% | prod | PXIPMX01 | 302PROD.txt
2 | Product Hierarchy | 303 |  | Chris | 0 | LADS | PX | IN |  | 100% | 100% | 100% |  | 100% | 100% | 100% | 50% | 0% | 0% | Prod | PXIPMX02 | 303PRODHIER.txt
3 | Customer | 300 | Ready to test | Mal | 0 | LADS | PX | IN |  | 100% | 100% | 100% |  | 100% | 100% | 100% | 50% | 0% | 0% | prod | PXIPMX03 | 300CUST.txt
4 | Customer Hierarchy | 301 | Validate data | Chris | 3 | LADS | PX | IN |  | 100% | 100% | 100% |  | 100% | 100% | 100% | 50% | 0% | 0% | test | PXIPMX04 | 301CUSTHIER.txt
5 | Vendor | 347 | Ready to test | Mal | 0 | LADS | PX | IN |  | 100% | 100% | 100% |  | 100% | 100% | 100% | 50% | 0% | 0% | prod | PXIPMX05 | 347VEND.txt
6 | Pricelist | 330 | Ready to test | Mal | 0 | LADS | PX | IN |  | 100% | 100% | 100% |  | 100% | 100% | 100% | 50% | 0% | 0% | prod | PXIPMX06 | 330PRICELIST.txt
7 | AR Claims - ATLAS to LADS |  |  | Mal | 1 | ATLAS | LADS | IN |  | 100% | 100% | 100% |  | 90% | 90% | 100% | 0% | 0% | 0% | test | ATLCIS06.2
8 | AR Claims | 361 | Awaiting Test | Mal | 2 | LADS | PX | IN |  | 100% | 100% | 100% |  | 90% | 90% | 100% | 0% | 0% | 0% | test | PXIPMX08 | 361DEDUCT.txt
9 | Sales |  |  | Mal | 0 | Venus | LADS | IN |  | 100% | 100% | 100% |  | 100% | 100% | 100% | 0% | 0% | 0% | prod | PXIPMX07 | 306SALES.txt
10 | Sales | 306 |  | Mal | 0 | LADS | PX | IN |  | 100% | 100% | 100% |  | 100% | 100% | 100% | 0% | 0% | 0% | prod |  |  |  | 32
11 | Scan | 322 | Manual |  |  | na | na | IN | na | na | na | na |  | na | na | na | na | na | na | na | na | na | na | na | na
12 | Off Invoice actuals | 336 | PX Interface Screenshot | Mal | 3 | LADS | PX | IN |  | 100% | 100% | 100% |  | 100% | 100% | 100% | 0% | 0% | 0% | test | PXIPMX09 | 336PCACT.txt
13 | Efex (Payments) | New (502) | Manual |  |  | na | na | IN | na | na | na | na |  | na | na | na | na | na | na | na | na | na | na | na | na
14 | Costs | 363 | Manual |  |  | na | na | IN | na | na | na | na |  | na | na | na | na | na | na | na | na | na | na | na | na
15 | Promotion (pricing conditions) |  | Awaiting Test | Jon | 5 | PX | LADS | OUT |  | 100% | 100% | 70% |  | 80% | 80% | 0% | 0% | 0% | 0% | test | PMXATL04
16 | Promotion (pricing conditions) | 359 |  | Jon | 6 | LADS | ATLAS | OUT |  | 100% | 100% | 70% |  | 80% | 80% | 0% | 0% | 0% | 0% | test | PXIATL04
17 | Accruals |  | Specifying | Jon | 7 | PX | LADS | OUT |  | 100% | 100% | 100% |  | 30% | 30% | 0% | 0% | 0% | 0% | test | PMXLAD01
18 | Accruals - ATLAS | 325 |  | Jon | 8 | LADS | ATLAS | OUT |  | 100% | 100% | 100% |  | 30% | 30% | 0% | 0% | 0% | 0% | test | PXIATL01
19 | AP Claims |  | Awaiting Test | Jon | 1 | PX | LADS | OUT |  | 100% | 80% | 50% |  | 80% | 30% | 0% | 0% | 0% | 0% | test | PMXPXI02
20 | AP Claims - ATLAS | 331 |  | Jon | 2 | LADS | ATLAS | OUT |  | 100% | 80% | 50% |  | 80% | 30% | 0% | 0% | 0% | 0% | test | PXIATL01
21 | AR Claims |  |  | Jon | 3 | PX | LADS | OUT |  | 100% | 80% | 50% |  | 80% | 30% | 0% | 0% | 0% | 0% | test | PMXPXI02
22 | AR Claims - ATLAS | 331 |  | Jon | 4 | LADS | ATLAS | OUT |  | 100% | 80% | 50% |  | 80% | 30% | 0% | 0% | 0% | 0% | test | PXIATL01
23 | Demand | 337 | passthrough to be created | Jon | 9 | PX | LADS | OUT |  | 100% | 100% | 100% |  | 100% | 100% | 0% | 0% | 0% | 0% | test | PXIDFN01.4
24 | Demand | 337 |  | Chris | 0 | LADS | DF | OUT |  | 100% | 100% | 100% |  | 100% | 100% | 100% | 0% | 0% | 0% | test | PXIDFN01.4
25 | Demand Extract |  | Ready to test | Chris | 0 | DF | Apollo | OUT |  | 100% | 100% | 100% |  | 100% | 100% | 100% | 0% | 0% | 0% | test
26 | Demand - Table Maint |  | Ready to test | Chris | 0 | DF | DF | OUT |  | 100% | 100% | 100% |  | 100% | 100% | 100% | 0% | 0% | 0% | test
| Scripting On PX |  | Not this weekend | Craig
Dedmand - Auto draft to Forecast
Demand

## Issues Questions
Issue Num | Int ID | Date Raised | Issue/Question | Resolution | Date Resolved | Status
1 | 23 | 2013-07-25 | What is extracted? Base and uplift? | Stephen has confirmed | 2013-07-26 | Complete
2 | 13 | 2013-07-25 | is there any changes required for ap and ar claims when we start interfacing efex payments? | Stephen has confirmed the data will be the same between the manual ap creation and the efex payments interface | 2013-07-26 | Complete
3 | 23 | 2013-07-25 | Awaiting confirmation of part week as part of extract | Confirmed that PX manages the date range. | 2013-07-26 | Complete
4 | 6 | 2013-07-25 | Confirm with Emma she is happy with pricelist |  |  | Open
5 |  | 2013-07-25 | Interfacing should be to DB server. Install endpoint and install application Server name: mfants5.mfa.ap.mars | Email sent to BAI for new endpoint creation |  | Open
|  | 2013-07-25 | What is coming through in 337,base & uplift? | Resolved , data is a summation of base and uplift | 2013-07-26 | Complete
|  | 2013-07-25 | Issue loading Promax Estimates files to IPS FLU oracle Bug | Testing the issue |  | Open
|  | 2013-07-25 | Test Venus DB link to Prod for PXIPMX07 | Created and tested |  | Closed
|  | 2013-07-25 | Daily sales transactional data files currently overwrite | Needs to be taken into account with PX scriptiing |  | Open
6 |  | 2013-07-27 | Pricelist using MFA tables - should be rewritten | Tactically work round it. If have time revisit |  | Open
7 |  | 2013-07-27 | Confirm business process to change list proce start date, don’t change it. int 330 point 1.3.8.3 | Need to reiterate with business |  | Open
8 |  | 2013-07-27 | Figure out approach for loading historic zreps to match historic sales | Resolve after interfaces |  | Open
9 |  | 2013-07-27 | Figure out getting historic Customers in to match historic sales | Resolve after interfaces |  | Open
10 |  | 2013-07-27 | Sales daily - process for catching missed days |  |  | Open
11 |  | 2013-07-27 | If sales are moved between periods will not be re interfaced. | Agree with business |  | Open
12 |  | 2013-07-27 | Someone to look at BDS_MATERIAL_HDR check why MARS_RPRSNTTV_ITEM_FLAG is not populated | For information
13 |  | 2013-07-27 | Estimates file - material 232351 is not set up as a traded unit. This needs to be corrected by the business |  |  | Open
14 |  | 2013-07-27 | Confirm that we send new materials, old materials are handled in Promax. | Craig to raise with Emma / stephen |  | Open
15 |  | 2013-07-27 | Confirm with business that they are happy to have base units per sellable hard coded to 1. If not provide examples where it would be different. | Craig to raise with Emma |  | Open
16 |  | 2013-07-27 | Check with business that duplicated product (multiple different types of RSU for a TDU) will not cause an issue | Raise to business |  | Open
17 |  |  | Can we take the 0 records out of the demand extract.
18 |  | 2013-07-27 | Need to distribute a planning system that is not limited to 64000 rows | For information |  | Open
19 |  | 2013-07-28 | Follow up Gordo to ensure ATLCIS6.1 has been arranged to be split to a new interface to LADS for Promax PX. | Jon to follow up with Gordo. |  | Open
20 |  | 2013-07-28 | Raise with business viability of blocking negatives in interfaces | Craig to raise |  | Open
21 |  | 2013-07-28 | Confirm if the constant for the record type for the product hierachy interface should be 303002 or 303001. List price has 330002 and 330001 | Jon to raise with Stephen |  | Open
22 |  | 2013-07-28 | 336 Pricing conditions actuals - Condition_type field needs to be confirmed with business. Is it statis (170534) | Jon to raise with Emma / Martin |  | Open
23 |  | 2013-07-28 | Promotions / pricing conditions cancellations, business transaction field is the starting position to discuss with Nathan Schubert - failing that COE. | Jon to attempt to resolve with Nathan. If not follow up with COE to get technical version of the truth |  | Open
24 |  | 2013-07-28 | Follow up AMI re: triggering for interface out of PX | Jon |  | Open
25 |  | 2013-07-28 | Process for loading up one off data load for Test then Prod.
26 |  | 2013-07-28 | Grant execute on all packages to LICS_APP | Chris |  | Open
27 |  | 2013-07-28 | Error trapping in all packages | Chris / Mal |  | Open
28 |  | 2013-07-30 | DF - user friendly method to identify issues with Accounts and materials when load fails.l | Jon |  | Open
29
30

## Sheet1
'0040008072','0040007994','0040007938'